## Sheet1
| Total Past Due | Part Number | Desc | Qty
Qty of Units | 60 | 8348M1 | GEAR BOX ASSY. | 24
Value |  | 8372M2 | MLG VERTICAL SHAFT ASSY. | 21
|  | 3354379-2 | RAMP SIDE RAIL ASSEMBLY | 8
|  | 8681 | ACTUATOR ASSY. | 2
|  | 8526 | ACTUATOR ASSY | 2
|  | 8555M9 | LANDING LIGHT | 2
|  | 370983-8 | BEAM ASSEMBLY TROOP SEAT | 1

## Sheet2
Total Past Due
| Qty of Units | 57
| $ Value | 259494
| Root Cause |  |  | Corrective Action
Gear Box Assy | 1) Gear Cutter Down 2) 3 Mo Delay in Spider Mat'l |  | Gear Box Assy | • Age of the machine was a factor. It was going to take 20-22 weeks for the machine to be repaired. • The cam and a few other parts would have had to be made special. • Our PM service provider was called out immediately to try and repair the machine. But, because of the age and lack of parts they were not able to do so. • The manufacturer was then called in and that’s when we were told about the 20-22 weeks for repair. • John located another machine in California that we purchased. We are keeping the old machine for parts. • Purchasing has been tasked to outsource gear cutting jobs as needed. • As with all machines in the shop the gear cutter is on a regular PM schedule.